## Project_Schedule
PROJECT STATUS DASHBOARD - DATA ENTRY FORM
REPORTING PERIOD:
PROJECT NAME: | STRAT EDGE LINKAGES & PARTNERSHIPS |  |  | TOTAL BUDGET: | 750000
PROJECT NUMBER: | SE-PRJ-2026-01 |  |  | START DATE: | 2026-03-01
CLIENT: | Strat Edge Group |  |  | TARGET END DATE: | 2026-08-30
PROJECT MANAGER: | Admin |  |  | STATUS: | Active
PROJECT SCHEDULE (BASELINE PLAN)
Activity ID | Activity | Output | Planned Start | Planned End | Budgeted Cost (R) | Depends On | Actual Start | Actual End | Person Responsible
1 | Stakeholder Analysis & Mapping | Stakeholder Matrix | 2026-03-01 | 2026-03-10 | 25000 | - | 2026-03-02 |  | admin
2 | Partnership Framework Design | Framework Document | 2026-03-11 | 2026-04-05 | 85000 | 1 |  |  | pm_user
3 | Linkage Strategy Development | Strategy Report | 2026-04-06 | 2026-05-15 | 120000 | 2 |  |  | pm_user
4 | Compliance & Internal Submission | Compliance Certificate | 2026-05-16 | 2026-06-10 | 45000 | 3 |  |  | recorder
5 | Implementation of Shared Platform | Platform Go-Live | 2026-06-11 | 2026-07-30 | 250000 | 4 |  |  | pm_user
6 | Final Review & Handover | Contract Completion | 2026-08-01 | 2026-08-30 | 50000 | 5 |  |  | admin

## Expenditure_Log
EXPENDITURE LOG
Date | Activity ID | Category | Description | Reference (Invoice/PO) | Amount (R)
2026-03-05 | 1 | Consultancy | Stakeholder meeting fees | INV-881 | 12000
2026-03-08 | 1 | Travel | Regional site visits | EXP-042 | 4500

## Risk_Register
RISK REGISTER
Date Identified | Risk/Issue Description | Impact (H/M/L) | Status | Mitigation Action
2026-03-01 | Delay in stakeholder responses | M | Open | Send follow-up reminders
2026-03-04 | Compliance framework update | H | Open | Consult with legal team