## Project_Schedule
PROJECT STATUS DASHBOARD - DATA ENTRY FORM
REPORTING PERIOD:
PROJECT NAME: | LINKAGES&PARTNERSHIPS |  |  | TOTAL BUDGET: | 0
PROJECT NUMBER: | SE2 |  |  | START DATE: | 2026-03-01
CLIENT: | MTHASHANA TVET COLLEGE |  |  | TARGET END DATE: | 2026-08-30
PROJECT MANAGER: | SINQOBILE SHOBA |  |  | STATUS: | Active
PROJECT SCHEDULE (BASELINE PLAN)
Activity ID | Activity | Output | Planned Start | Planned End | Budgeted Cost (R) | Depends On | Actual Start | Actual End | Person Responsible
1 | Project Initiation & Kick-off | Approved Project Charter; Confirmed Governance Structure; Agreed Priority Sectors | 2026-02-23 | 2026-03-01 | 0
2 | Strategic Alignment & Policy Mapping | Strategic Alignment Matrix; Priority Sector Skills Map | 2026-02-24 | 2026-03-01 | 0 | 1
3 | Stakeholder & Ecosystem Mapping | Stakeholder Register; AI Partner Longlist; Engagement Strategy | 2026-02-25 | 2026-03-01 | 0
4 | Enabling Company Profile Development | Executive Company Profile (Draft); Sector Profile Variants; Digital Profile Structure | 2026-02-26 | 2026-03-01 | 0
5 | AI & Digitisation Setup | Digital Partnership Platform (Live); AI Partner Scoring Dashboard | 2026-02-27 | 2026-03-01 | 0
6 | Industry Engagement Preparation | Priority Partner Shortlist; Engagement Packs; Confirmed Meeting Schedule | 2026-03-02 | 2026-03-08 | 0
7 | Relationship Building Sessions | Engagement Records; Partnership Opportunity Notes | 2026-03-03 | 2026-03-08 | 0
8 | Pre-Agreement Development | Draft LoI Templates; Draft Conditional MoUs; Partnership Commitment Matrix | 2026-03-04 | 2026-03-08 | 0
9 | Validation & Governance Alignment | Validated Pre-Agreements; Risk Register; Governance Approval Notes | 2026-03-05 | 2026-03-08 | 0
10 | Reporting & Forward Planning | Inception Report; Approved Implementation Plan; M&E Framework | 2026-03-06 | 2026-03-08 | 0
11 | Review 1, Compliance & Submission | Final Bid Submission | 2026-03-09 | 2026-03-12 | 0
12 | Review 2, Compliance & Submission | Final Bid Submission | 2026-03-10 | 2026-03-12 | 0
13 | Review 3, Compliance & Submission | Final Bid Submission | 2026-03-11 | 2026-03-12 | 0
14 | Review 4, Compliance & Submission | Final Bid Submission | 2026-03-12 | 2026-03-12 | 0

## Expenditure_Log
EXPENDITURE LOG
Record every payment made. Attach invoice/PO reference.
Date | Activity ID | Category | Description | Reference (Invoice/PO) | Amount (R)

## Risk_Register
RISK & ISSUES REGISTER
Date Identified | Risk/Issue Description | Impact (H/M/L) | Status | Mitigation Action