Below is a clear, charter-aligned risk register for the 3-week implementation plan, with risks identified, ranked (High / Medium / Low impact) and specific mitigation actions.
This is written in formal project-governance language and is suitable for inclusion in the Project Charter, Inception Report, or Tender Risk Section.

Source: Project Charter – Implementation of the TVET Industry Linkages & Partnerships Framework (especially Section 4.2 Risk Mitigation and the 3-Week Workplan on pages 6–8)

RISK REGISTER – 3-WEEK INTENSIVE IMPLEMENTATION PHASE

1. HIGH IMPACT RISKS

(Risks that can materially delay or compromise delivery of the 3-week plan)

| Risk ID | Risk Description | Impact Level | Affected Activities | Mitigation Action |
| --- | --- | --- | --- | --- |
| H1 | Delayed availability or engagement of key College decision-makers during Week 1 | High | Project initiation, governance confirmation, strategic alignment | Confirm meeting dates in advance; nominate alternates; use written approvals where physical attendance is not possible |
| H2 | Low or delayed response from targeted strategic industry partners during Week 2 | High | Relationship building, pre-agreements, LoIs | Use pre-identified partner shortlists; leverage Strat Edge Solutions’ existing networks; issue conditional LoIs where full sign-off is pending |
| H3 | Misalignment between College expectations and framework scope identified late | High | Company profile development, pre-agreements | Conduct scope validation on Day 1; formal sign-off of objectives and deliverables; maintain change-control discipline |
| H4 | Failure to secure minimum viable pre-agreements within the 3-week window | High | Tender value-add deliverables | Use phased commitments (LoIs, expressions of support); secure written intent even where operational details follow later |
| H5 | Data or access constraints affecting AI-enabled partner identification | High | Stakeholder mapping, AI & digitisation setup | Use parallel data sources (SETAs, chambers, public registries); apply manual validation where AI data is incomplete |

2. MEDIUM IMPACT RISKS

(Risks that may cause rework or partial delays but are manageable)

| Risk ID | Risk Description | Impact Level | Affected Activities | Mitigation Action |
| --- | --- | --- | --- | --- |
| M1 | Incomplete or inconsistent policy inputs (DHET, SETA, PGDS) | Medium | Strategic alignment & sector prioritisation | Use latest approved versions; validate assumptions with College; document policy interpretation decisions |
| M2 | Limited availability of internal College data for Company Profile development | Medium | Company profile and value proposition | Use proxy data; include data gaps transparently; commit to updates post-inception |
| M3 | Scheduling conflicts during executive roundtables and engagement sessions | Medium | Relationship building (Week 2) | Conduct smaller targeted sessions; use virtual engagements where required |
| M4 | Delays in internal review and approval of draft pre-agreements | Medium | Validation & governance alignment | Parallel legal/governance review; early circulation of templates |
| M5 | Over-compression of activities leading to stakeholder fatigue | Medium | Week 2 & Week 3 activities | Prioritise high-value engagements; stagger sessions; manage expectations clearly |

3. LOW IMPACT RISKS

(Risks with limited effect on overall success if managed)

| Risk ID | Risk Description | Impact Level | Affected Activities | Mitigation Action |
| --- | --- | --- | --- | --- |
| L1 | Minor formatting or branding issues in early draft deliverables | Low | Company profile, reports | Apply quality assurance checks; final branding applied before submission |
| L2 | Short turnaround for bid document revisions in Week 3 | Low | Finalisation & submission | Use version control; allocate dedicated review resources |
| L3 | Technology configuration issues with digital tools | Low | AI & digitisation setup | Use lightweight tools initially; migrate to full systems post-inception |
| L4 | Availability of international partners during the 3-week phase | Low | International linkage scoping | Focus on pipeline development rather than final agreements |
| L5 | Minor dependency overlaps between activities | Low | Scheduling | Apply agile task sequencing and daily stand-ups |

SUMMARY RISK POSITION (FOR GOVERNANCE REPORTING)

- High Impact Risks: Managed through early validation, relationship leverage, and phased commitments

- Medium Impact Risks: Controlled through parallel processing and stakeholder management

- Low Impact Risks: Addressed through standard project controls

Overall, the 3-week plan is assessed as LOW-TO-MODERATE RISK, provided that governance discipline, early engagement, and phased partnership commitments are applied, as outlined in the Project Charter .

Next steps (optional)

I can:

- Convert this into a formal Risk Register table (Excel / Word)

- Add risk owners and monitoring indicators

- Align this directly to PMBOK or PRINCE2 risk formats

- Insert this into your Project Charter or Inception Report

Just tell me the format you need.